## Knowledge Coverage Report
Coverage ID | DPR Chapter | Knowledge Domain | Primary Evidence Source | Coverage Level | Evidence Status | Missing Evidence | Priority | Action Required | Owner | Remarks
KCR-001 | Executive Summary | Project Narrative | Master Reference | High | Available |  | Low | Validate narrative | PMO
KCR-002 | Project Description | Project Narrative | Master Reference | High | Available |  | Low | Confirm authority | PMO
KCR-003 | Site Analysis | Drawings & Images | Drawing Package | Medium | Partial | Approved drawing set | High | Select controlled drawings | Design
KCR-004 | Aquaculture Engineering | AQ-201/202/203 | Technical Reports | Medium | Partial | Engineering sign-off | High | Technical validation | Engineering
KCR-005 | CAPEX / BOQ | Finance | Financial Models | Low | Insufficient | Validated BOQ | Critical | Reconcile BOQ | Finance
KCR-006 | Financial Statements | Finance | Financial Models | Low | Insufficient | Authoritative model | Critical | Select baseline workbook | Finance
KCR-007 | Legal & Approvals | Corporate | Reference Package | Low | Partial | Land/permits | Critical | Collect due diligence evidence | Legal
KCR-008 | Risk & Implementation | Registers | Workspace | Medium | Available | Final review | Medium | Complete register | PMO