## Repository Certification
Certification Item | Current Status | Evidence | Required Action | Owner | Target Before DPR | Final Status | Remarks
Repository Inventory | Complete | Inventory & Manifest | None | PMO | Yes | Complete
Repository Governance | Complete | Governance documents | None | PMO | Yes | Complete
Knowledge Register | Complete | RKR | Maintain | PMO | Yes | Complete
Authoritative Source Register | In Progress | ASR | Complete authority selection | PMO | Yes | Open
Knowledge Coverage | In Progress | KCR | Close evidence gaps | PMO | Yes | Open
Repository Gap Closure | Open | Gap Report | Resolve critical gaps | All Teams | Yes | Open
Financial Workbook Authority | Not Certified | Finance Register | Select validated baseline | Finance | Mandatory | Open | Critical
Repository Certification Decision | NOT CERTIFIED | Audit Findings | Reassess after gap closure | Project Board | Mandatory | Pending | Lender-ready certification deferred