## Repository Gap Report
Gap ID | Knowledge Domain | Gap Description | Impact | Priority | Required Evidence | Responsible Team | Target Resolution | Status | Dependency | Remarks
GAP-001 | Financial Model | No authoritative workbook selected | Cannot produce lender-ready financials | Critical | Validated master workbook | Finance | Before DPR Financial Chapters | Open | ASR-005
GAP-002 | CAPEX / BOQ | BOQ not reconciled | CAPEX uncertainty | Critical | Approved BOQ | Engineering/Finance | Before Financial Validation | Open
GAP-003 | Drawings | Controlled drawing set not identified | Design inconsistency | High | Approved drawing register | Engineering | Before DPR Design Chapters | Open
GAP-004 | Legal | Land/approval evidence incomplete | Due diligence risk | Critical | Land & statutory approvals | Legal | Before Certification | Open
GAP-005 | Environmental | Compliance evidence incomplete | Approval risk | High | Validated environmental records | Environment | Before Certification | Open
GAP-006 | Narrative | Revision conflicts | Potential inconsistencies | Medium | Authority confirmation | PMO | Knowledge Extraction | Open